## Migration Checklist
Phase | # | Checklist Item | Details | Status | Owner | Due Date | Notes
Phase 1: Discovery and Data Audit
Phase 1 | 1 | Evaluate current help desk and document pain points | Define what is broken, slow, or frustrating. These become success criteria for the migration. | Not Started
Phase 1 | 2 | Define migration goals and measurable success criteria | Set specific targets like 'reduce resolution time by 20%' or 'support 3x ticket volume.' | Not Started
Phase 1 | 3 | Identify all stakeholders and assign a single project owner | One person must own the project end-to-end for accountability and decision-making. | Not Started
Phase 1 | 4 | Complete a full data inventory across all object types | Catalog tickets, contacts, orgs, KB articles, custom fields, tags, attachments, agent accounts. | Not Started
Phase 1 | 5 | Capture exact record counts for every data object | Run exports or API queries. You need precise counts to validate after migration. | Not Started
Phase 1 | 6 | Map dependencies between data objects | Tickets depend on contacts, contacts link to orgs, automations reference custom fields. Know the order. | Not Started
Phase 1 | 7 | Run data profiling on source data | Measure null rates, duplicate rates, orphan records, and encoding anomalies per field. | Not Started
Phase 1 | 8 | Decide what to migrate, archive, or discard | Spam tickets, test data, duplicates, deprecated fields, outdated KB articles should not move. | Not Started
Phase 1 | 9 | Identify all custom fields, tags, and picklist values needing mapping | Export a complete list. Each needs a mapping rule: 1-to-1, transform, or retire. | Not Started
Phase 1 | 10 | Document all active automations, triggers, macros, SLA policies, routing rules | These must be manually rebuilt. Document every trigger condition, action, and dependency. | Not Started
Phase 1 | 11 | List every third-party integration connected to current help desk | CRM, billing, Slack, analytics, phone, chatbot. Each must be reconnected and tested. | Not Started
Phase 2: Strategy and Planning
Phase 2 | 12 | Select migration strategy: Big Bang, Phased, or Trickle | Big Bang = downtime OK. Phased = batches. Trickle = zero downtime with delta sync. | Not Started
Phase 2 | 13 | Create a RACI matrix for the migration project | Define Responsible, Accountable, Consulted, Informed for each phase. | Not Started
Phase 2 | 14 | Define rollback criteria and rollback procedure | Decide what failure looks like and how to reverse it before you start. | Not Started
Phase 2 | 15 | Set acceptable data variance and error rate thresholds | Targets: row parity >= 99.9%, error rate <= 0.5%, zero orphan records. | Not Started
Phase 2 | 16 | Build a detailed project timeline with milestones | Assign calendar dates to each phase. Typical mid-market migration: 4-8 weeks. | Not Started
Phase 2 | 17 | Add a 15-20% contingency buffer to the timeline | Every migration surfaces surprises. Contingency is best practice, not pessimism. | Not Started
Phase 2 | 18 | Create a migration budget covering all cost categories | Subscription, migration labor, training, productivity dip, contingency fund. | Not Started
Phase 2 | 19 | Build a communication plan for every stage | Who gets notified at each milestone? What are the escalation paths? | Not Started
Phase 2 | 20 | Get formal stakeholder sign-off on strategy, timeline, and budget | Written approval from sponsors, IT leadership, and support management. | Not Started
Phase 3: Data Preparation and Mapping
Phase 3 | 21 | Clean source data: remove spam, test records, duplicates | Run deduplication. Delete spam and test tickets. Migrating dirty data defeats the purpose. | Not Started
Phase 3 | 22 | Merge duplicate contacts and organizations | Same email, different names = duplicates. Merge before migration to avoid split histories. | Not Started
Phase 3 | 23 | Archive tickets older than your retention policy | Reduces volume, speeds migration, keeps new system clean. Archive separately for compliance. | Not Started
Phase 3 | 24 | Perform a full backup of your source system | Export everything: database, attachments, KB content, configuration. This is your safety net. | Not Started
Phase 3 | 25 | Verify backup by restoring to an isolated test environment | A backup you have not tested is not a backup. Attempt a partial restore to confirm. | Not Started
Phase 3 | 26 | Store backup in a secure, separate location | S3, GCS, Azure Blob, or encrypted local drive. Not inside either platform. | Not Started
Phase 3 | 27 | Create a versioned field mapping document | Source field -> target field -> transform rule. Example: Product_Line (multi-select) -> product_tag (text). | Not Started
Phase 3 | 28 | Document all data transformation logic in detail | Field concatenation, picklist conversion, date formats, timezone normalization, JSON flattening. | Not Started
Phase 3 | 29 | Get field mapping reviewed by a business owner or support lead | Engineers check technical correctness. Business owners check operational sense. | Not Started
Phase 3 | 30 | Create a test dataset for pilot migration runs | Include your most complex records: longest threads, most custom fields, deepest nesting. | Not Started
Phase 3 | 31 | Commit mapping specification to version control | Every mapping change must be tracked. Use Git or equivalent. | Not Started
Phase 4: Platform Setup and Configuration
Phase 4 | 32 | Set up new help desk platform instance | Account, subdomain, branding (logo, colors, email templates). Complete before any data import. | Not Started
Phase 4 | 33 | Configure user roles and permissions in the new system | Recreate permission structure: admin, agent, supervisor, read-only roles. | Not Started
Phase 4 | 34 | Recreate all custom fields, tags, statuses, and picklist values | These must exist in the target before data import. Missing fields = silent data loss. | Not Started
Phase 4 | 35 | Rebuild automation rules, triggers, workflows, and macros | Cannot be migrated as data. Use Phase 1 documentation as blueprint. Test each individually. | Not Started
Phase 4 | 36 | Rebuild SLA policies and escalation rules | Response time targets, escalation paths, business hours. No SLA enforcement on day one without this. | Not Started
Phase 4 | 37 | Configure email channels with proper DNS records | Set up forwarding rules. Verify SPF, DKIM, DMARC. Incorrect config = missing tickets on day one. | Not Started
Phase 4 | 38 | Configure chat, messaging, and social media channels | Live chat, Messenger, WhatsApp, Twitter DMs. Channel-specific routing may need separate config. | Not Started
Phase 4 | 39 | Set up all third-party integrations | Reconnect CRM, billing, analytics, Slack, phone. Regenerate API keys/OAuth tokens for new platform. | Not Started
Phase 4 | 40 | Create all agent accounts and verify login access | Every agent must log in before go-live. Discover login issues 48 hours early, not on cutover day. | Not Started
Phase 4 | 41 | Distribute training materials and quick-reference guides | One-page cheat sheets for common tasks: reply, assign, escalate, use macros. | Not Started
Phase 4 | 42 | Hold training sessions or office hours for agents | At least one hands-on session plus open office hours for questions. | Not Started
Phase 5: Sample Migration and Pilot Testing
Phase 5 | 43 | Run a sample migration on test dataset | Start with the most complex records. If hard data works, easy data will too. | Not Started
Phase 5 | 44 | Validate ticket threading and conversation integrity | Verify threads display in correct order: customer messages, agent replies, internal notes. | Not Started
Phase 5 | 45 | Validate custom field values and tag mappings | Spot-check transformed values. A picklist value should not be blank or 'Unknown.' | Not Started
Phase 5 | 46 | Verify all attachments transferred and are openable | Check files are present AND can be opened. Silent attachment failures are common. | Not Started
Phase 5 | 47 | Verify historical timestamps are preserved | Created On and Modified By should show original dates, not migration date. | Not Started
Phase 5 | 48 | Verify relational integrity between objects | Tickets linked to correct contacts. Contacts linked to correct orgs. Zero orphans. | Not Started
Phase 5 | 49 | Check encoding for special characters, emoji, multi-byte strings | Search for emoji and accented characters. Verify they display correctly in target. | Not Started
Phase 5 | 50 | Measure row parity: source count vs target count per object type | Any discrepancy must be investigated and explained before proceeding. | Not Started
Phase 5 | 51 | Test the rollback procedure on sample data | Purge test data from target and verify source is unaffected. | Not Started
Phase 5 | 52 | Run additional sample migrations until all issues resolved | Do not proceed until every known issue is fixed and re-validated. | Not Started
Phase 5 | 53 | Document all issues found and fixes applied | Log every issue: what went wrong, root cause, how it was fixed. | Not Started
Phase 6: Go-Live Cutover Execution
Phase 6 | 54 | Announce code and configuration freeze on both platforms | 48 hours before cutover. No deployments, no workflow changes, no permission edits. | Not Started
Phase 6 | 55 | Revoke write access on both systems during freeze window | Restrict admin/developer roles to read-only to prevent accidental changes. | Not Started
Phase 6 | 56 | Hold final Go/No-Go meeting with unanimous stakeholder approval | Any unresolved concern is a No-Go. Do not proceed with lingering doubts. | Not Started
Phase 6 | 57 | Perform final full backup of source system | Last safety net. Back up complete database and all attachments. | Not Started
Phase 6 | 58 | Verify final backup with a partial restore test | Confirm backup is not corrupted and is restorable in an isolated environment. | Not Started
Phase 6 | 59 | Execute bulk data migration | Run production pipeline. Monitor rows processed, rows failed, error logs, throughput. | Not Started
Phase 6 | 60 | Monitor migration progress and error logs in real time | Watch for 429 (rate limit), 413 (payload), 422 (validation) errors. | Not Started
Phase 6 | 61 | Place old help desk in read-only mode | Disable email forwarding, API endpoints, chat widgets, customer portal on source. | Not Started
Phase 6 | 62 | Post read-only banner in old system UI | Inform agents the old system is read-only. Include link to new system. | Not Started
Phase 6 | 63 | Execute final delta migration | Catch-up script captures all data created since bulk migration started. Enables zero downtime. | Not Started
Phase 6 | 64 | Run post-delta validation checks | Row parity, aggregate totals, checksums, referential integrity between source and target. | Not Started
Phase 6 | 65 | Re-point DNS and all incoming support channels to new system | Email forwarding, MX records, chat widgets, API webhooks, portal DNS. | Not Started
Phase 6 | 66 | Enable notifications and automations in new system | Only AFTER data validation is complete. Premature activation fires on partial data. | Not Started
Phase 6 | 67 | Re-establish and test all third-party integrations | Reconnect every integration. Send test data through each one. | Not Started
Phase 6 | 68 | Send test messages through every support channel | Test email, chat, portal. Confirm each creates a ticket and routes correctly. | Not Started
Phase 7: Post-Migration QA and Hypercare
Phase 7 | 69 | Spot-check ticket data from different time periods | Random tickets from last week, last month, last year, 2+ years ago. | Not Started
Phase 7 | 70 | Verify contact and organization records | Names, emails, phones, org links, custom fields on a sample. | Not Started
Phase 7 | 71 | Verify knowledge base articles | Content, formatting, images, categories, URL slugs. | Not Started
Phase 7 | 72 | Verify attachment and file integrity | Open sample attachments. Confirm correct files, not corrupted. | Not Started
Phase 7 | 73 | Test automation and trigger execution end-to-end | Create test ticket. Verify assignment rules, auto-responses, SLA timers fire. | Not Started
Phase 7 | 74 | Test SLA policies and escalation rules | Verify countdown timers, business hours, escalation thresholds. | Not Started
Phase 7 | 75 | Test all support channels end-to-end | Real email, real chat, real portal ticket through full lifecycle. | Not Started
Phase 7 | 76 | Have 2-3 agents complete a full workflow walkthrough | Pick up ticket, read history, reply, internal note, assign, resolve, close. | Not Started
Phase 7 | 77 | Test customer portal | Submit ticket, view history, search KB as a customer. | Not Started
Phase 7 | 78 | Validate reporting dashboards and historical analytics | Dashboards display data. Historical reports show accurate numbers. | Not Started
Phase 7 | 79 | Benchmark performance against pre-migration baseline | Page load, API response, search speed. Target: within +/-20% of baseline. | Not Started
Phase 7 | 80 | Audit user roles, permissions, and security settings | Correct roles, correct access levels, no over-permissioned users. | Not Started
Phase 7 | 81 | Set up war room or dedicated Slack channel for hypercare | Single place for agents to report issues. Staff with someone who can triage. | Not Started
Phase 7 | 82 | Send company-wide go-live communication | Notify entire company. Include links to new system and quick-reference guides. | Not Started
Phase 7 | 83 | Monitor error rates, latency, missing-record alerts for 48-168 hours | Error rate <0.5%, latency +/-20%, missing records = 0, retries <2%. | Not Started
Phase 7 | 84 | Gather real-time agent feedback daily | Pulse survey or daily standup. What is not working? What is confusing? | Not Started
Phase 7 | 85 | Hold post-mortem review and document lessons learned | What went well, what went wrong, what to do differently next time. | Not Started
Phase 7 | 86 | Begin decommissioning old system | Archive data, secure wipe, terminate subscription, update CMDB. | Not Started